Training Proposal

TEC Group — AI training for sales & marketing

| PREPARED FOR Kevin Kinzie CEO / Co-Founder, TEC Group kevin@tecgrouprep.com 281-210-7420 www.tecgrouprep.com | PREPARED BY Steven Hughes heysteve.ca hughes.steven@outlook.com 1-519-498-8239 Kitchener, Ontario |
| --- | --- |

Date: May 4, 2026

What this is

A four-week, hands-on AI training program for your sales and marketing team (5–10 people). The goal isn't to teach AI in the abstract — it's to leave every attendee using AI tools every day in their actual work, with a small library of prompts and habits they own going forward.

No software development in this engagement. Just training, hands-on practice on real TEC Group work, and a written playbook your team keeps updating after I'm gone.

What I understand you're after

Audience: 5–10 people on the sales and marketing teams.

Goal: they use AI tools more confidently and effectively in their day-to-day work — research, outreach, content, follow-up, internal docs.

Scope: training only for this engagement. No custom build.

Format: four sessions, one per week, over four weeks.

If any of that is off, tell me on the kickoff call and I'll adjust.

Approach — four sessions

Every session follows the same shape: ~30 min concept, ~45 min hands-on with real TEC Group work that attendees bring, ~15 min Q&A. Live and remote (Zoom or Google Meet). Recordings and slides shared after each session.

Session 1 — Foundations & first wins (Week 1)

What today's tools (Claude, ChatGPT, Gemini, Perplexity) actually do well, and where they fall over.

A simple mental model: treat AI as a sharp research analyst and writer who has zero context about your company until you give it some.

Hands-on: each attendee brings two real tasks from their inbox or backlog. We knock them out together using AI.

Walk-away: three reusable prompts each person will use this week.

Session 2 — Sales workflows (Week 2)

Prospect and account research at scale — turning a list of 20 accounts into qualified briefs in 30 minutes.

Personalized outreach drafting that doesn't read like spam.

Pre-call prep, follow-up notes, summarizing transcripts.

Hands-on: each rep builds their own pre-call brief template against a live opportunity.

Walk-away: a saved prompt template each rep will use weekly.

Session 3 — Marketing workflows (Week 3)

Drafting blog posts, case studies, LinkedIn, email — and editing the output so it doesn't sound AI-written.

Repurposing one piece of content into five formats without doubling the work.

Brand voice: how to feed AI enough context that it writes like TEC Group and not like a generic chatbot.

Hands-on: each marketer builds a TEC Group voice prompt and applies it to a piece of in-progress content.

Walk-away: a documented brand-voice prompt the marketing team reuses.

Session 4 — Tools, integration, and sustainable habits (Week 4)

Beyond the chat box: Claude Projects, custom GPTs, AI inside the CRM and email tools your team already uses.

Cost and data hygiene — what's safe to paste, what isn't, and how to think about it.

Building a one-page internal AI playbook for TEC Group — the prompts, habits, and guardrails your team will keep updating after I'm gone.

Group Q&A and review of what each person took away.

Walk-away: a TEC Group AI playbook, drafted live in the session, owned by your team.

What your team gets

Four 90-minute live sessions over four weeks.

Recordings of every session.

All slides, prompts, and templates used.

Email/Slack access between sessions for follow-up questions.

A written one-page TEC Group AI playbook your team owns and maintains.

Logistics

Group size: 5–10 attendees from sales and marketing.

Schedule: one 90-minute session per week, same day and time each week.

Format: live remote (Zoom or Google Meet); recordings provided.

Start date: mutually agreed; typically two weeks from go-ahead.

What I'll need from you

A weekly time slot that works for the team.

One point of contact on your side for scheduling and follow-up.

Real examples of the work your team is doing — account lists, drafts, emails, briefs — so the hands-on portions are practical, not theoretical.

Investment

| Item | Amount |
| --- | --- |
| Standard four-week training program | $25,000 |
| First-engagement discount (50%) | – $12,500 |
| Total for this engagement | $12,500 |

Terms. 50% ($6,250) on signing to confirm the start date, 50% ($6,250) on completion of session four. Invoiced in USD.

This is a fixed-fee engagement. No hourly billing, no scope creep surprises — if a session runs long, that's on me.

Why this scope, why this price

The standard $25,000 engagement assumes some level of custom work — a prompt library tailored to your existing tools, deeper integration help, or a small build. This proposal is training-only, four sessions, one team. The 50% discount reflects that narrower scope and the fact that this is our first engagement together.

If down the line you want to build something specific — a custom assistant trained on TEC Group's product catalog, a sales-research workflow that runs every Monday morning, anything in that direction — we can scope it separately.

Next steps

Reply yes (or with questions) by reply email.

I'll send a short kickoff form: team list, scheduling preferences, what AI tools each person has already tried.

We pick a start date and I send the invoice for the first 50%.

Session one happens about two weeks later.

I'd be glad to do this work. Looking forward to hearing back.

— Steven

hughes.steven@outlook.com  ·  1-519-498-8239  ·  heysteve.ca